## Sheet1
NOTE -OVERALL SYSTEM IS VERY SLOW ALSO AUTOMETIC CHANGES AT DIFFERENT FIELDS ARE REPORTED
| Dept | Issues | Solution | Points by Bharathbrands
1 | Registration screen | PHOTO | Mandatory
NHIF/INS ID
|  | MEMBER ID |  | All ID we can capture in existing app.
|  | Pt no and next of kin no can not be same |  | Member ID is new requirement
|  | National ID |  | validation check to be provided for pt and next of kin no
EMAIL ID
|  | unable to edit insurace/NHIF bill once finalized | Need rights to admin users for edit the bill | Bill Editing will be based on some assumption, need to discuss before giving rights.
|  | finalized/closed bills show(India) country name in registration window | it should be on autometic generated based on phone no | Its done
2 | Open bill | in open bill - unable to see pharmacy bill for ins/nhif client | pharmacy bill should reflect to finalize the bill | currently only bill header is coming .detail pharmacy bill can be viewed from pharmacy module.
3 | Cancel bill | Unable to write a reason for cancel bill | Need Dialogue box for reason to cancel | To be provided from BB.
| Pharmacybill | unable to open pharmacy detailed bill | need to link pharmacy detailed bill in opening detailed view | Alisha to clarify the details. | Alisha to clarify the details with screen and function, what type of detailed bill in screen or report..
4 | OPD Billing | Without Putting payment details bill generated autometically - eg -UHID2309110748 (2 times automatic registred) | STRICTLY NO BILL TO BE GENERATED & CLOSE- without Payment details | Alisha to clarify the points for ins/nhif patients
5 | Payment | M-pesa mode- at times we have 2 or 3 refernce no of payments | Multiple (minimum 3) fields of MPESA payments | Point not clear, Alisha to clarify
6 | Credit Note | not available for patient service | must required | Pls provide format for credit note
7 | Pharmacy / Procurement | Medicine details is not coming with full name | Category like inj,tab and strength eg 250mg, 100mg- should be coming | To be provided from BB.
8 | Pharamcy | Provision of quotation/estimate is not available | It is for NHIF/Insurance quotation is mandatory | TO be provided from BB. | Alisha to brief in detail about the quatation for more clarification.
9 | Laboratory | Monthly lab report for All Pt | Mandatory for Doc - the format was shared with Daniel | Pls provide format for monthly format.
10 | Laboratory | Unable to send Lab report via email | Autometic upload of lab report should be activate and sent | Its done. BB to brief lab team.
11 | Laboratory | Lab summary Report for ,sample collection,test done & reporting time and report emailed & the errors if any | Need to select date ranges | To be provided from BB.
12 | Laboratory (Master Rights for Admin) | Need Rights how to add test ranges , template & Interpretation | As per MOH incase of any new test we need to add ranges also templates and interpretation | Alisha has been given access, rest other users will be given based on authorozation by nephromed.
13 | Laboratory | No of individual test done each month | Need to select date ranges | we have common report for individual and profile
14 | Procurement | Goods Return to the supplier - missing in the Procurement module | Mandatory | Supplier return is there in system.
15 | Procurement | frequently used item also not reflecting in Purchase report eg Epo, iron | all purchase item should reflect on purchase item report | Alisha to clarify further.
16 | Procurement | in LPO item name coming with (general,medicine) | Category should not show with item | To be provided from BB.
17 | Procurement | making lpo -1st time coming error, in 2nd time lpo process going | error should not reflect | need to be checked realtime, user to inform kalai
18 | Report | Doctor calculation report | still pending since long (discussed on 14/6 with Dharmendra and reminder on 26/8/23) | Doctor share report incorporated.
19 | Master | How to add packages | Provide traning and rights to Admin to avoid delays & resolve locally
|  | How to add insurances |  | Training be provided from BB.
How to add lab test and their ranged
20 | Daybool- collection summary report | Need date ranges on report |  | its there, in printing we will enable.
21 | HR MODULE | Pending | Needed ASAP | to be provided from BB.document upload pending only.
22 | Finance Module |  |  | Not in Scope
23 | DR Module | Dr is not able to see client until bill closed from Registration | after creating pt visit - dr should be able should reflect | AS per our discussion, consultation billing has to be done for all patient, to avail consultation.
|  | Diagnosis detais not captured after filled |  | To be checked by BB
|  | Results are not showing | Need to merge lab result with doc prescribed test | POINT DONE
|  | History and examination data not captured after filled |  | To be checked by BB
|  | Advice details not capturing after filled |  | To be checked by BB
|  | Nurse Seen, Doctor Seen, Visit complete button are not working |  | To be checked by BB
|  | After prescribing medicinr by dr- it's reflecting with different bill no | should be same visit no and bill no - registred by admin | To be checked by BB. Alisha to clarify further
24 | Consultant window | need date time , dept and phone no of pt,, remove bill id |  | To be done by bb
25 | Nephrology | in dialysis report chart - INTRA DIALYSIS ASSESSMENT row is missing | must needed as per MOH | Done as per format provided.
|  | Remove Admijusitedc drug row |  | Done as per format provided.
26 | Oncology | Module is missing- it was before |  | Done as per format provided.
27 | Master | Add and delete users and their rights | Provide traning and rights to Admin to avoid delays & resolve locally | Training be provided from BB.